## Sheet1
CEW OEL: To develop an environmental monitoring system that retrieves real-time environmental data
Work Breakdown Structure
Tasks | Executor | Status | Deadline
Data Retrieval |  |  | 2023-12-16
Research available free APIs for real-time environmental data. | Tooba | Done
Evaluate the suitability of each API based on data availability and compatibility with the project requirements. | Tooba | Done
Select the most appropriate API for retrieving real-time environmental data. | Mehwish | Done
Set up the necessary environment and dependencies for API integration. | Aqiba | Done
Implement the functionality to make API requests and retrieve environmental data. | Aqiba | Done
Test API integration and ensure the retrieved data is accurate and in the expected format. | Mehwish | Done
Data Processing and Analysis |  |  | 2023-12-18
Determine the necessary data processing steps required for cleaning and preprocessing the retrieved data. | Tooba
Implement algorithms to clean and preprocess the raw environmental data. | Mehwish
Identify the key parameters and metrics for analyzing the processed data. | Aqiba
Develop algorithms to analyze the processed data and identify anomalies or trends. | Tooba
Test the data processing algorithms and ensure they correctly clean and preprocess the data. | Mehwish
Test the data analysis algorithms and verify their accuracy in identifying anomalies or trends. | Aqiba
Data Storage |  |  | 2023-12-22
Determine the appropriate file formats and structures for storing the raw and processed environmental data. | Mehwish | Done
Implement file handling functionality to create and write the raw environmental data to a file. | Tooba | Done
Design the structure for storing processed data and implement file handling functionality to write the processed data to separate files. | Aqiba | Done
Test the data storage modules and verify that data is stored accurately in the designated files. | Mehwish | Done
Reporting System |  |  | 2023-12-24
Define the layout and structure of the reports to be generated based on the analyzed environmental data. | Tooba
Implement the necessary functions to generate reports using the processed data. | Mehwish
Develop templates and formatting mechanisms for generating reports in a readable and visually appealing manner. | Aqiba
Test the reporting system and ensure that the generated reports accurately reflect the analyzed environmental data. | Tooba
Automation and Integration |  |  | 2024-12-28
Identify the repetitive tasks within the system that can be automated. | Mehwish
Create shell scripts to automate data retrieval, processing, and report generation tasks. | Tooba
Integrate the shell scripts with the main program to enhance automation and streamline the workflow. | Aqiba
Test the automation and integration modules and verify that tasks are executed correctly and efficiently. | Mehwish
Optimization and Efficiency |  |  | 2024-01-01
Analyze the codebase to identify areas for optimization in terms of memory usage and computational efficiency. | Aqiba
Utilize pointers and dynamic memory allocation to optimize data manipulation and storage. | Tooba
Implement the identified optimizations in the relevant parts of the code. | Mehwish
Test the optimized code and measure the performance improvements achieved through the implemented optimizations. | Aqiba
Real-time Alerts |  |  | 2024-01-03
Determine the critical environmental readings that require real-time alerts. | Tooba
Implement the necessary functions to trigger alerts based on predefined thresholds. | Aqiba
Integrate the alerts with the reporting system to ensure timely notification of critical readings. | Mehwish
Test the real-time alert system and verify that alerts are triggered correctly when critical readings occur. | Tooba
Documentation and Code Organization |  |  | 2024-01-04
Create detailed documentation that includes installation instructions, usage guidelines, and API documentation. | Tooba
Organize the code into modularized functions and separate header files to enhance code readability and maintainability. | Mehwish
Review the documentation and code organization to ensure clarity, completeness, and adherence to coding standards. | Aqiba